## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Abikrishna P. | NEEDS USER INPUT | Missing values in numerical project features were not handled before feature preparation, causing errors during model training. | S1 | Abikrishna P. | Missing-value handling issue | Added explicit imputation step for numerical features before training. | NEEDS USER INPUT | Closed
2 | Abikrishna P. | NEEDS USER INPUT | Unseen categorical values encountered during inference were not handled by the encoding logic used for categorical features. | S2 | Abikrishna P. | Categorical feature processing issue | Updated the categorical encoding step to handle unseen categories gracefully at inference time. | NEEDS USER INPUT | Closed
3 | Abikrishna P. | NEEDS USER INPUT | Model prediction endpoint returned inconsistent risk scores when input feature order did not match the order used during training. | S3 | Abikrishna P. | Model prediction issue | Enforced a fixed feature order/schema between the FastAPI request payload and the CatBoost model input. | NEEDS USER INPUT | Closed
4 | Abikrishna P. | NEEDS USER INPUT | FastAPI prediction endpoint did not validate incoming request fields, allowing malformed input to reach the model. | S3 | Abikrishna P. | API integration issue | Added request schema validation using Pydantic models for the prediction endpoint. | NEEDS USER INPUT | Closed
5 | Abikrishna P. | NEEDS USER INPUT | Streamlit dashboard did not refresh prediction results correctly when a user submitted a new project record for risk analysis. | S4 | Abikrishna P. | Streamlit UI issue | Corrected session-state handling in Streamlit so the dashboard re-renders with the latest prediction result. | NEEDS USER INPUT | Closed
6 | Abikrishna P. | NEEDS USER INPUT | Frontend did not display an error message when the FastAPI backend was unreachable, leaving the dashboard in a blank state. | S4 | Abikrishna P. | Frontend-backend communication issue | Added error handling in the Streamlit app to show a user-facing message when the backend API call fails. | NEEDS USER INPUT | Closed

## Sheet2
Logical
User Interface
Maintainability
Standards
Others